## Summary
DOH Review Comments (via Xylee “XJ” Javier) — Findings & Fixes Summary
ASPSI–DOH UHC Survey Year 2 CAPI · compiled 2026-08-14 · statuses verified against the current build
What this file covers
• XJ's PAPI-vs-CAPI screenshot reviews (July 2026) — 149 per-question findings: 63 on HCW (F2) and 86 on Household (F4). Each finding is one row on the instrument tabs, with XJ's comment verbatim and the current-build status.
• The DOH June-2026 questionnaire comment batch (also relayed via XJ) for F1/F3/F4 — summarized at theme level on the F1/F3/F4 tabs. Per Dr. Myra Silva-Javier's ruling (2026-06-12) these are PARKED: the April-20 questionnaire is the accepted build baseline.
• DOH-agreed content changes that WERE built (PhilHealth follow-up reinstatements; June-5 Deliverable-2 tool alignment) — rows marked 'Fixed in build'.
Key result of the August 2026 verification
• All 88 'Other (specify) field missing' findings were re-audited against the live instruments: 85 verified present (50 F4 dictionary fields, 35 F2 PWA companion fields with required 'Please specify' validation) and 3 not applicable (F2 Q109 is free-text; F2 Q112/Q123 have no Other option). 0 real gaps.
• Multi-select exclusivity (an XJ ask on both instruments) now HARD-blocks invalid combinations — shipped class-wide in the pretest fix waves (Aug 2026).
• The remaining design/UX/process items need no build change: they are answered by documentation (skip/validation matrix + test login + current screenshots), are deliberate design, or await an ASPSI/DOH decision (parked).
How to read the Status column
• Fixed in build — a change was made and deployed. • Verified in build — the asked-for feature already exists (confirmed by audit).
• Already in build — feature existed before the review; XJ's April screenshots pre-date it. • By design — intentional difference from PAPI, rationale documented.
• Docs to provide — no build change; answered via the evidence pack. • Parked — DOH decision — change candidate held per the 2026-06-12 ruling.
Counts by status
Status | F1 | F2 | F3 | F4 | Total
Fixed in build | 0 | 0 | 2 | 3 | 5
Verified in build | 0 | 35 | 0 | 50 | 85
Already in build | 0 | 8 | 0 | 8 | 16
By design | 0 | 2 | 0 | 4 | 6
Docs to provide | 0 | 7 | 0 | 3 | 10
Parked — DOH decision | 1 | 8 | 1 | 20 | 30
Not applicable | 0 | 3 | 0 | 0 | 3
Total rows | 1 | 63 | 3 | 88 | 155

## Facility Head (F1)
Facility Head (F1) — DOH comments via XJ
XJ's July-2026 PAPI-vs-CAPI screenshot review covered F2 and F4 only — no per-question XJ findings exist for F1. Rows below are the F1 items from the DOH June-2026 questionnaire comment batch (relayed via XJ), per-item matrix held in ASPSI's comment thread/Google Doc.
Question | Comments | Category of bug | Fixes | Status | GitHub ref
Q19, Q21, Q23, Q25, Q27, Q29, Q31, Q39–Q48 (+ EMR / MoU / NBB / ZBB items) | DOH proposed restructuring ~18 questions into a two-step pattern: “Has this changed since 2019?” then “Is the change a result of the UHC Act?”. | Questionnaire redesign (content) | No build change — parked per Dr. Myra Silva-Javier's ruling (2026-06-12): the April-20 questionnaire is the accepted baseline; June comments are answered with finality only if they resurface via SJREB review, PSA review, or pre-testing. Adopting them mid-stream was quantified (2026-06-19) as an 8–10-week slip. | Parked — DOH decision | —

## HCW (F2)
Healthcare Worker (F2 / PWA) — 63 XJ findings
Source: XJ PAPI-vs-CAPI HCW review (July 2026), triaged one GitHub issue per finding under epic #849 (label from-doh-review-xj-2026-07). Comments are XJ's, verbatim from the triage. Statuses re-verified against the current PWA build, August 2026.
Question | Comments | Category of bug | Fixes | Status | GitHub ref
form-wide | The HCW Survey CAPI appears to use a different interface. Clarify whether a different platform/version is used and the rationale; consider consistent UX across instruments. (XJ rates the HCW/PWA interface the more polished one — section headers, progress indicators, no repeated question text.) | Form structure / sections | Working as designed — F2 is the PWA by design (self-administered, online/offline); F1/F3/F4 are CSPro. Document the rationale; XJ recommends the others match F2, not the reverse. | By design | #851
documentation | Since the tools were submitted to PSA, documentation should reflect the complete/near-final CAPI; representative screenshots of full interface + functionality across instruments would enable a more accurate review. | Process / documentation | No build change — to be answered with the evidence pack (skip/validation matrix + test login). Evidence: supply current screenshots + a test login. | Docs to provide | #852
sections | The submitted screenshots do not show the Questionnaire number, Informed Consent Form, Field Control, and Health Facility & Geographic Identification sections present in PAPI. Clarify how implemented in CAPI, and whether the offline version matches the online interface. | Form structure — consent | Already implemented in the current build — Consent gate shipped (F2 R6 #808); enrolment carries facility/QN. Screenshot gap — attach current screens; state offline parity. No code change needed; evidence = current screens. | Already in build | #853
navigation | Screenshots do not show navigation controls. Clarify how respondents navigate, especially when reviewing/correcting previous responses. | Platform behavior / UX | Already implemented in the current build — PWA has section navigation. Screenshot/documentation gap. No code change needed; evidence = current screens. | Already in build | #854
autosave | Clarify whether the app autosaves on connectivity loss, device interruption, or unexpected closure, and describe data-recovery mechanisms. | Platform behavior / UX | Already implemented in the current build — F2 has IndexedDB autosave in production. Document it. No code change needed; evidence = current screens. | Already in build | #855
resume | Clarify whether the system can detect an incomplete questionnaire and allow resuming from the last saved point. | Platform behavior / UX | Already implemented in the current build — F2 supports resume in production. Document it. No code change needed; evidence = current screens. | Already in build | #856
timeout | Indicate whether sessions time out/expire; if so, how unsaved responses are handled and whether users are notified before expiry. | Platform behavior / UX | Working as designed — Design point — state the behaviour (self-administered PWA). | By design | #857
required-fields | The HCW CAPI uses a red asterisk (*) to mark fields but provides no legend. If it marks required fields, add a brief note clarifying its meaning. | Display / wording | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Small UX add; candidate. | Parked — DOH decision | #858
skip-matrix | Skip rules are omitted from the interface (correct for CAPI) but the reviewer cannot verify programmed skips/validations without test access, and screenshots don't demonstrate validation checks. Provide a skip-pattern matrix, programming specs, or a test environment. | Process / documentation | No build change — to be answered with the evidence pack (skip/validation matrix + test login). Highest-leverage answer: one skip/validation matrix + a test login (verify_questions.py output is a starting point). | Docs to provide | #859
validation-exclusive | For multiple-answer questions, automatically block selecting 'None of the above'/'Refuse'/'Not applicable'/'Don't know' if 'Other (Specify)' or any listed option is chosen. | Validation — answer rules | Already implemented in the current build — the PWA enforces exclusivity (selecting a listed/Other option blocks or clears exclusive options), shipped before the review and covered by automated exclusivity tests. Evidence = current-build demo. | Already in build | #860
validation-simultaneous | For multiple-answer questions, prevent simultaneous selection of the exclusive options (None/Refuse/NA/DK). | Validation — answer rules | Already implemented in the current build — mutually-exclusive options cannot be selected together in the PWA; enforcement predates the review. Evidence = current-build demo. | Already in build | #861
validation-single-multi | Check for questions needing only one answer where the program allows multiple selection, and vice versa. | Validation — answer rules | No build change — to be answered with the evidence pack (skip/validation matrix + test login). Verify via the validation matrix. | Docs to provide | #862
employment-defs | The employment-type definitions in PAPI are not shown in CAPI. As it is self-administered, make definitions available (help text/tooltips). | Display / wording | Already implemented in the current build — Shipped as the #826 newline-rendered Q2 definitions. Confirm current render. No code change needed; evidence = current screens. | Already in build | #863
select-one | The PAPI 'Select one answer only' instruction is not observed in CAPI. Confirm whether intentionally omitted or enforced by the interface. | Validation — answer rules | No build change — to be answered with the evidence pack (skip/validation matrix + test login). Enforced by single-select controls; confirm. | Docs to provide | #864
input-labels | For numeric responses with units, add input labels like 'Year(s)'/'Day(s)'/'Hour(s)' as in Q9; Q10 (days) and Q11 (hours) lack them. | Display / wording | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Candidate UX; verify current labels. | Parked — DOH decision | #865
Q38 | For Q38, clarify whether 'Not a physician/dentist' can be determined automatically from the respondent's role in Q5; if so, implement as a system-driven condition rather than a manual option. | Clarification / process | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Candidate logic change; ASPSI/DOH call. | Parked — DOH decision | #866
E1 | No sub-header 'E1. Awareness of and perceptions on BUCAS' shown in CAPI. | Form structure / sections | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Presentation; add section sub-header. | Parked — DOH decision | #867
E2 | No sub-header 'E2. Awareness of GAMOT Package' shown in CAPI. | Form structure / sections | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Presentation; add section sub-header. | Parked — DOH decision | #868
Q62 | Is the 'proceed to Q63...' a typo that should be 'proceed to Q62'? Who will answer Q62 given the skip rules in Q61? | Display / wording | No build change — to be answered with the evidence pack (skip/validation matrix + test login). Verify routing against spec; confirm/correct. | Docs to provide | #869
Q71 | Will 'yes' in Q69 and 'yes' in Q70 have a separate input field for Q71 as shown in PAPI? | Clarification / process | No build change — to be answered with the evidence pack (skip/validation matrix + test login). Verify against spec/build. | Docs to provide | #870
Q35 | The CAPI Q35 provides clearer instructions (Year required; Month/Day optional) — an improvement over PAPI. Apply the same design consistently where applicable. | Display / wording | Already implemented in the current build — Positive — XJ praises this; note as the model to reuse. No code change needed; evidence = current screens. | Already in build | #871
Q98 | Missing instruction before Q98, applicable up to Q107. | Display / wording | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Add the section instruction; verify. | Parked — DOH decision | #872
Q113 | Missing instruction before Q113, applicable up to Q120. | Display / wording | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Add the section instruction; verify. | Parked — DOH decision | #873
Q6 | Q6 has no screenshot in CAPI. | Clarification / process | No build change — to be answered with the evidence pack (skip/validation matrix + test login). Screenshot gap; attach current screen. | Docs to provide | #874
form-wide | A 'None' option appears added in CAPI (unspecified item) — confirm whether intended. | Clarification / process | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Verify the item; confirm. | Parked — DOH decision | #875
Q2 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q2 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q2_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #912
Q5 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q5 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q5_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #913
Q6 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q6 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q6_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #914
Q13 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q13 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q13_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #915
Q15 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q15 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q15_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #916
Q17 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q17 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q17_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #917
Q18 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q18 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q18_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #918
Q19 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q19 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q19_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #919
Q20 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q20 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q20_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #920
Q21 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q21 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q21_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #921
Q22 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q22 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q22_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #922
Q23 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q23 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q23_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #923
Q24 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q24 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q24_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #924
Q25 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q25 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q25_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #925
Q34 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q34 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q34_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #926
Q36 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q36 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q36_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #927
Q37 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q37 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q37_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #928
Q39 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q39 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q39_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #929
Q42 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q42 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q42_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #930
Q43 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q43 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q43_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #931
Q45 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q45 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q45_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #932
Q46 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q46 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q46_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #933
Q47 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q47 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q47_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #934
Q50 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q50 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q50_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #935
Q52 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q52 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q52_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #936
Q55 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q55 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q55_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #937
Q56 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q56 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q56_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #938
Q57 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q57 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q57_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #939
Q60 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q60 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q60_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #940
Q62 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q62 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q62_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #941
Q92 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q92 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q92_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #942
Q93 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q93 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q93_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #943
Q94 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q94 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q94_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #944
Q109 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q109 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | Not applicable — Q109 is a free-text question in the current instrument (no answer options, so no 'Other' to specify). | Not applicable | #945
Q110 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q110 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q110_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #946
Q112 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q112 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | Not applicable — Q112 has no 'Other (specify)' option in the current instrument. | Not applicable | #947
Q123 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q123 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | Not applicable — Q123 has no 'Other (specify)' option in the current instrument. | Not applicable | #948
Q124 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q124 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the PWA schema) — companion field Q124_other exists with a required 'Please specify' validation when Other is chosen. | Verified in build | #949

## Patient (F3)
Patient (F3) — DOH comments via XJ
XJ's July-2026 PAPI-vs-CAPI screenshot review covered F2 and F4 only — no per-question XJ findings exist for F3. Rows below: F3 items from the DOH June-2026 comment batch (parked) plus DOH-driven changes that WERE built.
Question | Comments | Category of bug | Fixes | Status | GitHub ref
Q38.1 / Q38.2 | DOH-agreed reinstatement of the PhilHealth registration follow-ups: when the respondent registered/received the PIN (Q38.1) and why not registered (Q38.2). (Separate DOH-agreed batch, not part of the parked June comments.) | DOH-agreed content change | Fixed — built and deployed to CSWeb during UAT Round 5 (GitHub #764, closed 2026-06-26, deployed 06-27). Live in the F3 dictionary as Q38_1_PIN_WHEN and Q38_2_WHY_NOT_REG (tick-all). “I don't know” follows the locked missing-value standard (−98). | Fixed in build | #764
Q92, Q96, Q107, Q109 | Payment-source matrices: amount-bearing sources reordered to the top, and Q109 gains a “Donation” option — changes DOH adopted into the June-5 English tool that ships inside Deliverable 2 (the version the pretest testers held and all 7 translations were made from). | Value sets / question order | Fixed — CAPI aligned to the June-5 Deliverable-2 tool in F3 v2.0.0, deployed 2026-08-13 (tickets #1151/#1152/#1156/#1158). Breaking data-shape change handled: codebook regenerated; tabulation owner flagged (code-keyed breakdowns); pretest-case remap expected. | Fixed in build | #1151–#1158
After Q18 (new block); Q24–Q28; items #168–171 | June-2026 batch: add a new household-expenditure block after Q18; replace Q24–Q28 with the FIES asset battery; add billed-vs-paid amount items (#168–171). | Questionnaire redesign (content) | No build change — parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 baseline). Revisited only if the ask resurfaces via SJREB / PSA / pretest, or if it already appears in the June-5 Deliverable-2 tool (which is checked before deferring any “the paper says X” ticket). | Parked — DOH decision | —

## Household (F4)
Household (F4 / CSPro) — 86 XJ findings + DOH-driven changes
Source: XJ PAPI-vs-CAPI Household review (July 2026), triaged one GitHub issue per finding under epic #850 (label from-doh-review-xj-2026-07). Comments are XJ's, verbatim from the triage. Statuses re-verified against the current F4 dictionary/generators, August 2026.
Question | Comments | Category of bug | Fixes | Status | GitHub ref
Q45.1 / Q45.2 | DOH-agreed reinstatement of the PhilHealth registration follow-ups: when the respondent registered/received the PIN (Q45.1) and why not registered (Q45.2). (Separate DOH-agreed batch, not part of XJ's July review.) | DOH-agreed content change | Fixed — built and deployed to CSWeb during UAT Round 5 (GitHub #794 + #795, closed and deployed 2026-06-25). Live in the F4 dictionary as Q45_1_PIN_REG_WHEN and Q45_2_WHY_NOT_REG (+ _OTHER_TXT). | Fixed in build | #794 #795
Whole instrument | June-2026 batch (CONTESTED): DOH wants its April-15 PIDS/DHS-style household questionnaire restructure adopted; the UP/ASPSI team was instructed NOT to follow it. | Questionnaire redesign (content) | No build change — parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 baseline). XJ's own July screenshot review turned out clarification/observation-heavy, not the feared restructure. | Parked — DOH decision | —
consent | The Consent Form section from PAPI is not found in CAPI. | Form structure — consent | Already implemented in the current build — Consent/break-off handling exists; screenshot/clarify implementation. No code change needed; evidence = current screens. | Already in build | #876
field-control | Field Control appears at the end. Clarify whether these fields are completed only on completion or can be accessed/updated during the interview, particularly for incomplete interviews requiring callbacks and resumption. | Field control / visits | Already implemented in the current build — Break-off + disposition model handles this; document callback flow. No code change needed; evidence = current screens. | Already in build | #877
disposition | Justify the April change of 'Refused' to 'Withdraw Participation/Consent'; clarify category + code-order differences vs Facility/HCW forms (Completed, Postponed, Refused, Incomplete); harmonize unless intentional/documented. | Form structure — consent | Working as designed — Deliberate; document rationale + cross-instrument harmonization intent. | By design | #878
visit-date | The facility visit-date format differs (PAPI Month-Day-Year vs CAPI YYYYMMDD). Provide rationale. | Value sets / codes / formats | Working as designed — Design choice; document. | By design | #879
visits | Confirm how many visits are allowed; only first and final are recorded, but the manual allows up to three callbacks in the Visit Sheet. Clarify how intermediate visits/callbacks are documented in CAPI. | Field control / visits | No build change — to be answered with the evidence pack (skip/validation matrix + test login). Map callbacks to the CAPI break-off/disposition model; document. | Docs to provide | #880
navigation | Screenshots don't show navigation controls (Next/Back/Go-To/navigator). Clarify how enumerators navigate/correct previous responses. | Platform behavior / UX | Already implemented in the current build — CSEntry has built-in navigation. Documentation gap. No code change needed; evidence = current screens. | Already in build | #881
autosave | Clarify whether the app autosaves on connectivity loss/interruption/closure, and data-recovery mechanisms. | Platform behavior / UX | Already implemented in the current build — CSEntry partial-save. Document. No code change needed; evidence = current screens. | Already in build | #882
resume | Clarify whether the system can detect incomplete interviews and resume from the last saved point. | Platform behavior / UX | Already implemented in the current build — Partial-save resume. Document. No code change needed; evidence = current screens. | Already in build | #883
timeout | Indicate whether sessions time out; if so, how unsaved responses are handled and whether enumerators are notified. | Platform behavior / UX | Working as designed — Document behaviour. | By design | #884
QN | The Questionnaire Number is 9-digit in PAPI vs 12-digit in CAPI — flagged inconsistent. | Value sets / codes / formats | Working as designed — Deliberate cross-instrument 12-digit key (facility-9 + sequence-3). Document. | By design | #885
geo | The Household Address & Geographic ID section looks incomplete — only Classification + Barangay visible; Region/Province/City and lat-long not observed. Implement a cascading geo selection (Region -> Province/HUC -> City/Municipality -> Barangay) to narrow the barangay list and reduce mis-selection. | Geographic ID / GPS | Already implemented in the current build — CAPI gates the 12-digit key through a PSGC cascade. Verify the household-address presentation; attach current screens. No code change needed; evidence = current screens. | Already in build | #886
geocodes | A previous review said geocodes would be added; not reflected in screenshots. Clarify status/location, and how lat/long GPS is captured, recorded, and validated. | Value sets / codes / formats | Already implemented in the current build — GPS captured at end-of-flow (warm-radio); accuracy recorded. Document capture/validate. No code change needed; evidence = current screens. | Already in build | #887
repeated-text | Throughout the CAPI screenshots the question text appears displayed twice. Consider displaying it once. | Display / wording | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Presentation (CSPro prompt+field); candidate cleanup. | Parked — DOH decision | #888
section-titles | Section titles and introductions present/sequenced in PAPI are not consistently observed or appear out of order in CAPI. Retain them in intended sequence. | Form structure / sections | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Presentation; candidate. | Parked — DOH decision | #889
skip-matrix | Reviewer cannot verify programmed skips/validations without test access; screenshots don't demonstrate validation checks. Provide a skip-pattern matrix, programming specs, or test-environment access. | Process / documentation | No build change — to be answered with the evidence pack (skip/validation matrix + test login). Same high-leverage answer as F2: matrix + test login. | Docs to provide | #890
validation-exclusive | For multiple-answer questions, block 'None'/'Refuse'/'NA'/'Don't know' if 'Other (Specify)' or any listed option is chosen. | Validation — answer rules | Fixed — at the time of XJ's review the F4 exclusivity check was a soft warning; it now HARD-blocks the combination (exclusive options like None / I don't know / N/A cannot be kept alongside real answers), applied class-wide in the F4 generator (pretest fix wave #1075–#1080, 2026-08-05). | Fixed in build | #891
validation-simultaneous | For multiple-answer questions, prevent simultaneous selection of the exclusive options. | Validation — answer rules | Fixed — simultaneous selection of exclusive options is now hard-blocked class-wide (same generator guard; was a soft warning at review time; upgraded in the pretest fix wave, 2026-08-05). | Fixed in build | #892
validation-single-multi | Check questions needing only one answer that allow multiple selection, and vice versa. | Validation — answer rules | No build change — to be answered with the evidence pack (skip/validation matrix + test login). Verify via validation matrix. | Docs to provide | #893
travel-duration | For travel-duration questions, clarify the hour/minute limit. Year-1 SurveyCTO rejected >1440 minutes; Year-2 must allow travel time exceeding one day, particularly in GIDA households. | Clarification / process | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Verify the range validation; adjust if capped. | Parked — DOH decision | #894
automate-notes | Manual notes that should be system logic are still displayed. Convert to skip rules/eligibility/validation and remove from the enumerator view; contextualize retained notes for CAPI (e.g., 'tick'->'select'). | Clarification / process | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Broad presentation/logic cleanup; candidate. | Parked — DOH decision | #895
select-all | Clarify questions that appear to have a missing 'Select all that apply' instruction. | Display / wording | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Verify multi-select items; add instruction. | Parked — DOH decision | #896
Q1 | The instruction 'Ask all questions in this section unless a skip rule applies' appears retained at most questions (e.g. Q1). If all skips are programmed, this may be unnecessary; if kept as guidance, retain section titles/context. | Form structure / sections | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Presentation cleanup; candidate. | Parked — DOH decision | #897
Q15 | In Q15, clarify whether the list is external to CAPI; if incorporated, 'A list will be provided...' may be unnecessary. Q15 appears open-text — consider a dropdown/searchable selection to reduce encoding errors. | Clarification / process | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Candidate UX/data-quality change. | Parked — DOH decision | #898
Q18 | For Q18: the enumerator note for the first question (approximate amount) is not applicable and should be removed; the income-bracket note kept PAPI 'tick' (revise to 'select'); dropdown options not shown; consider auto-deriving the bracket from the amount entered. | Clarification / process | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Multiple candidate changes on one item. | Parked — DOH decision | #899
Q45.1/45.2/78/117/118 | For Q45.1, Q45.2, Q78, Q117, Q118 the PAPI filter instruction appears retained in the question text and may be misread as part of the question. Automate via display logic/skip rules, or clearly distinguish as an enumerator note (blue font/styling). | Display / wording | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Presentation; candidate. Verify these are programmed skips. | Parked — DOH decision | #900
Q57/Q69-73 | For Q57 and Q69-73, if eligibility is determinable from previously collected info (address), implement as an automated rule rather than a manual instruction. | Display / wording | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Candidate logic change. | Parked — DOH decision | #901
Q11-order | Inconsistent order of options for Q11. | Clarification / process | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Verify option order; align. | Parked — DOH decision | #902
Q22 | Inconsistent question for Q22 (house vs. household). | Display / wording | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Wording fix; verify. | Parked — DOH decision | #903
Q29 | No 'Refuse to answer' option in CAPI for Q29. | Clarification / process | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Verify; add if intended. | Parked — DOH decision | #904
Q103-opt | For Q103, missing option: 'No, I haven't accessed any form of medical care'. | Clarification / process | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Verify; add if intended. | Parked — DOH decision | #905
Q199-range | Amount range not shown for Q199. | Clarification / process | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Verify; add range. | Parked — DOH decision | #906
Q30-Q50 | Clarify the roster programming logic — is it a member-level loop (input a member, complete all applicable questions, then next member)? Add controls to prevent mixing/duplication across members; only Q48 seems to show the member name/roster line — confirm a member identifier is shown throughout. | Clarification / process | Already implemented in the current build — F4 uses the C_HOUSEHOLD_ROSTER repeating record; member-name display was addressed in the roster rebuild. Document the workflow. No code change needed; evidence = current screens. | Already in build | #907
roster-prefill | Respondent information already collected should auto-populate in the roster module, with the enumerator only confirming pre-filled info. | Value sets / codes / formats | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Candidate UX; verify prefill. | Parked — DOH decision | #908
Q67 | Q67 changed from a single HH:MM field to separate Hours and Minutes. Clarify whether they combine into one duration and stay consistent with PAPI; consider a grouped time field and displaying the main question once (currently repeated). | Clarification / process | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Candidate presentation/data-structure change. | Parked — DOH decision | #909
expenditure | The Household Expenditure translation repeats item/question text heavily, making the data elements (consumed / amount purchased / estimated in-kind value) hard to distinguish. Group all questions for a single item under one labeled screen with concise field labels. | Display / wording | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Candidate presentation redesign. | Parked — DOH decision | #910
Q186-Q194 | The section introduction, instructions, and overarching question for Q186-Q194 are not observed in CAPI, so items read as standalone Yes/No. Clarify whether displayed elsewhere; if not, retain. | Form structure / sections | No build change — change candidate parked per Dr. Myra Silva-Javier's ruling (2026-06-12; April-20 questionnaire is the accepted baseline); needs an ASPSI/DOH decision before building. Presentation/context; candidate. | Parked — DOH decision | #911
Q5 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q5 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q5_GROUP_OTHER_TXT. | Verified in build | #950
Q10 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q10 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q10_DISABILITY_OTHER_TXT. | Verified in build | #951
Q11 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q11 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q11_EDUCATION_OTHER_TXT. | Verified in build | #952
Q17 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q17 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q17_DECISION_MAKER_OTHER_TXT. | Verified in build | #953
Q23 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q23 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q23_WATER_OTHER_TXT. | Verified in build | #954
Q38 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q38 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q38_DISABILITY_OTHER_TXT. | Verified in build | #955
Q45.2 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q45.2 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q45_2_WHY_NOT_REG_OTHER_TXT. | Verified in build | #956
Q46 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q46 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q46_MEMBER_OTHER_TXT. | Verified in build | #957
Q52 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q52 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q52_UHC_SOURCE_OTHER_TXT. | Verified in build | #958
Q53 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q53 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q53_UHC_UNDERSTAND_OTHER_TXT. | Verified in build | #959
Q55 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q55 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q55_YAKAP_SOURCE_OTHER_TXT. | Verified in build | #960
Q56 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q56 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q56_YAKAP_UNDERSTAND_OTHER_TXT. | Verified in build | #961
Q58 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q58 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q58_BUCAS_SOURCE_OTHER_TXT. | Verified in build | #962
Q59 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q59 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q59_BUCAS_UNDERSTAND_OTHER_TXT. | Verified in build | #963
Q61 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q61 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q61_BUCAS_SERVICES_OTHER_TXT. | Verified in build | #964
Q65 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q65 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q65_CONDITIONS_OTHER_TXT. | Verified in build | #965
Q66 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q66 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q66_WHERE_BUY_OTHER_TXT. | Verified in build | #966
Q70 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q70 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q70_GAMOT_SOURCE_OTHER_TXT. | Verified in build | #967
Q71 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q71 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q71_GAMOT_UNDERSTAND_OTHER_TXT. | Verified in build | #968
Q74 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q74 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q74_WHERE_REST_OTHER_TXT. | Verified in build | #969
Q77 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q77 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q77_WHY_GENERIC_OTHER_TXT. | Verified in build | #970
Q78 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q78 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q78_WHY_BRANDED_OTHER_TXT. | Verified in build | #971
Q79 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q79 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q79_REG_SOURCE_OTHER_TXT. | Verified in build | #972
Q80 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q80 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q80_ASSIST_OTHER_TXT. | Verified in build | #973
Q82 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q82 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q82_DIFFICULTY_REASONS_OTHER_TXT. | Verified in build | #974
Q85 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q85 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q85_BENEFITS_OTHER_TXT. | Verified in build | #975
Q88 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q88 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q88_DIFF_PAYING_OTHER_TXT. | Verified in build | #976
Q91 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q91 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q91_WHY_WENT_OTHER_TXT. | Verified in build | #977
Q92 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q92 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q92_FACILITY_TYPE_OTHER_TXT. | Verified in build | #978
Q93 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q93 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q93_WHY_NOT_OTHER_TXT. | Verified in build | #979
Q94 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q94 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q94_TRANSPORT_OTHER_TXT. | Verified in build | #980
Q101 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q101 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q101_CHECKUP_FREQ_OTHER_TXT. | Verified in build | #981
Q102 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q102 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q102_VISIT_REASON_OTHER_TXT. | Verified in build | #982
Q103 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q103 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q103_CARE_TYPE_OTHER_TXT. | Verified in build | #983
Q106 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q106 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q106_FORGONE_WHY_OTHER_TXT. | Verified in build | #984
Q107 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q107 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q107_OTHER_ACTIONS, Q107_OTHER_ACTIONS_OTHER_TXT. | Verified in build | #985
Q109 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q109 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q109_TYPE_OTHER_TXT. | Verified in build | #986
Q110 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q110 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q110_SPECIALIST_OTHER_TXT. | Verified in build | #987
Q111 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q111 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q111_METHOD_OTHER_TXT. | Verified in build | #988
Q113 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q113 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q113_WHY_NOT_OTHER_TXT. | Verified in build | #989
Q121 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q121 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q121_WHY_HOSPITAL_OTHER_TXT. | Verified in build | #990
Q127 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q127 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q127_NBB_SOURCE_OTHER_TXT. | Verified in build | #991
Q128 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q128 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q128_NBB_UNDERSTAND_OTHER_TXT. | Verified in build | #992
Q133 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q133 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q133_ZBB_SOURCE_OTHER_TXT. | Verified in build | #993
Q134 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q134 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q134_ZBB_UNDERSTAND_OTHER_TXT. | Verified in build | #994
Q137 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q137 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q137_MAIFIP_SOURCE_OTHER_TXT. | Verified in build | #995
Q141 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q141 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q141_BILL_ITEMS_OTHER_TXT. | Verified in build | #996
Q143 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q143 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q143_HOW_PAID_OTHER_TXT. | Verified in build | #997
Q194 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q194 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q194_OTHER_SOURCE, Q194_OTHER_TXT. | Verified in build | #998
Q199 | XJ flags that all questions with an 'Other (specify)' option lack the 'specify' data field; Q199 is on that list. Ensure the 'Other' option exposes a free-text capture. | Data capture — Other (specify) field | VERIFIED in current build (2026-08 audit of the live F4 dictionary) — free-text capture present as Q199_WTP_OTHER_TXT. | Verified in build | #999